## Slide 1
Enhancing copies in the Core of Relational Databases
April 8th, 2022

## Slide 2: 01 – Previous meeting wrap up
02 – Task completion
03 – Current status
04 – Next steps

## Slide 3: 01
Previous meeting wrap up

## Slide 4
Initial ideas about how to avoid the creation of an infinity sampling for copying
Preliminary results on the convergence of a copy in the dual framework
Previous meeting comments

## Slide 5: 03
Current status

## Slide 6
Current Status
02
Hot and random start comparison
01
Improving the mathematical foundation of the problem

## Slide 7
Best fit parameter is estimated step by step as synthetic data is shown to the copy:
New mathematical framework
We have a proof of convergence for the parameter (can we validate it external experts?)
Data weights are still not included in the model (next steps)
Access to the overleaf: link

## Slide 8
Current Status
02
Hot and random start comparison
01
Improving the mathematical foundation of the problem

## Slide 9
Hot Start vs. random
N 2N 3N …
N = 30
The sample size increase linearly at each step
A hot-start approach shows a better performance
The sample size can be reduced by introducing the weights (next steps)

## Slide 10
Hot Start vs. random
N = 70

## Slide 11: 04
Next Steps

## Slide 12
Next Steps
02
Include weights to our model
01
External validation of the mathematical model (it will require some writing)
03
Validate copy process with weights and with new datasets (toy and real data)